PATATTE BACKEND

Production Database Migration

Deployment Documentation & Rollout Roadmap

Prepared by: Head of Infrastructure, Patatte

Scope: Test → Production schema migration

Status: DRAFT — for review

Last updated: [DATE]

# 1. Purpose & Ownership

The schema on the test environment has been updated and validated by the development team. A migration script exists to bring production from its current schema to that validated state. This document does not define or evaluate the migration script's contents — that is owned by the development team. It defines the deployment process around it: what Infrastructure needs from the dev team before execution, how the change is safely rolled out to production, how it is verified, and how it is rolled back if something goes wrong.

Ownership split Development team: writes, tests, and owns the correctness of the migration script. Infrastructure (this document): owns the production execution — backup, timing, environment readiness, monitoring, verification, and rollback. Infrastructure does not need to understand the internal logic of the script to safely own its deployment, provided the intake requirements in Section 2 are met.

## 1.1 Key concern

Production holds live data that does not exist on test. The primary risk is not whether the script works — it has presumably been validated on test — but whether running it against production causes data loss, extended downtime, or an inconsistent state if it fails partway through. This roadmap is built entirely around de-risking that gap.

# 2. Intake Requirements From Development

Before Infrastructure will schedule a production run, the development team provides the following. This is the handoff checklist — nothing proceeds to Section 4 until every row is checked.

| Item | Description | Received? |
| --- | --- | --- |
| Migration script / change set | The exact script(s) or migration files that will run against production | [ ] |
| Change summary | Plain-language list of what tables/fields are added, changed, or removed | [ ] |
| Breaking vs. additive flag | Which changes are backward-compatible and which are not | [ ] |
| Reversal method | How each change can be undone (reverse script, restore point, or 'not reversible') | [ ] |
| Test-environment run confirmation | Confirmation the script ran successfully end-to-end on test with production-representative data volume | [ ] |
| Estimated runtime | How long the script takes to execute against a dataset of production's approximate size | [ ] |
| Application dependency notes | Whether the new application release must deploy before, after, or simultaneously with the script | [ ] |

If any row is unchecked, the migration is not scheduled. This keeps Infrastructure from having to reverse-engineer risk from a script it didn't write.

# 3. Risk Classification

Based on the intake in Section 2, the change is classified below. This classification determines the deployment window, backup depth, and rollback readiness required in Sections 4–6.

| Category | Definition | Deployment implication |
| --- | --- | --- |
| Low risk | Purely additive — new tables/columns/indexes, no impact to existing rows or existing app behavior | Can run in a standard deployment window with a routine backup |
| Medium risk | Backward-compatible but touches existing data (e.g. backfilling a new column) | Requires a dedicated window, pre/post row-count verification, and a tested reversal path |
| High risk | Not backward-compatible while running (e.g. renamed/removed columns, type changes the running app can't tolerate) | Requires a maintenance window, application coordinated with the script per Section 2, full backup + restore test, and an active rollback owner on standby |

This migration's classification: [LOW / MEDIUM / HIGH — fill in from Section 2 intake].

# 4. Pre-Deployment Checklist

## 4.1 From development

- All items in Section 2 intake table are checked off

- Script has been reviewed for any operation that would lock large tables for an extended period

- Dev team has confirmed the script is idempotent or safe to resume if interrupted partway through

## 4.2 Data safety

- Full production backup taken and restore-tested against a scratch environment (Section 5)

- Pre-migration row counts / checksums captured for every affected table

- Recovery window confirmed (backup + any point-in-time recovery available from the database provider)

## 4.3 Environment readiness

- Production database version/configuration matches what the script was tested against on test

- Deployment pipeline for running the script has been dry-run against a non-production target

- Maintenance mode / traffic draining mechanism confirmed working, if required by the risk classification

## 4.4 People & communication

- Deployment window scheduled and communicated to stakeholders (Section 8)

- Rollback owner named and available for the full duration of the window: [Name]

- Development contact available on standby in case the script behaves unexpectedly: [Name]

# 5. Backup & Recovery Strategy

## 5.1 Pre-migration backup

Taken immediately before the deployment window starts, using your database platform's native backup mechanism (e.g. a managed snapshot, or a native dump/export tool appropriate to the database engine in use).

- Backup is copied off the primary host to separate, durable storage — not left only on the database server

- Backup is restore-tested against a scratch/staging instance before the migration proceeds

- Retention: kept for at least [30] days following the migration

## 5.2 Point-in-time recovery

Confirm whether the production database has point-in-time recovery or continuous backup enabled, and note the achievable recovery window here: [X hours/days]. If not available, the pre-migration snapshot is the sole recovery point — treat the risk classification in Section 3 accordingly.

## 5.3 Rollback triggers

Conditions under which the team aborts and rolls back rather than pushing forward:

- The migration script exits with an error or does not complete within its estimated runtime plus a reasonable buffer

- Post-migration verification (Section 6.3) does not match expected row counts or checksums

- Application error rate exceeds an agreed threshold in the first period after deployment

- Any unexpected data state is discovered in an affected table

# 6. Rollout Plan

## 6.1 Timeline

| Step | Action | Owner | Est. Duration |
| --- | --- | --- | --- |
| 1 | Freeze non-essential production deploys | Infrastructure | — |
| 2 | Announce deployment window start | Infrastructure | 5 min |
| 3 | Take and verify pre-migration backup (5.1) | Infrastructure | [X min] |
| 4 | Enable maintenance mode / drain traffic, if required by risk class | Infrastructure | 2 min |
| 5 | Execute migration script via deployment pipeline | Infrastructure | [X min — per dev estimate] |
| 6 | Run post-migration verification (6.3) | Infrastructure | 10 min |
| 7 | Deploy dependent application release, if applicable | Infrastructure | [X min] |
| 8 | Run smoke tests on critical flows (6.4) | Infrastructure | 15 min |
| 9 | Disable maintenance mode / restore traffic | Infrastructure | 2 min |
| 10 | Actively monitor error rates and logs | Infrastructure | 30–60 min |
| 11 | Announce completion | Infrastructure | 5 min |

## 6.2 Execution

The script is executed exactly as received from the development team via the standard deployment pipeline — Infrastructure does not alter script contents at execution time. Where the pipeline supports it, a dry-run/check pass is done first to preview the change without applying it. The pipeline must be configured to halt (not proceed to the application deploy step) if the migration step fails.

[deployment-pipeline] run migration --target=production --env=patatte-prod
# e.g. CI/CD job, orchestration tool, or platform-specific deploy command

## 6.3 Post-migration verification

Run immediately after the script completes, before disabling maintenance mode. Compare against the pre-migration baseline captured in Section 4.2.

- Row counts on every affected table match the pre-migration baseline (± only the expected new rows)

- Spot-check a sample of rows in any backfilled or transformed column against the source data

- No unexpected nulls in columns that are now required/non-nullable

- Referential integrity (foreign keys / relations) validates cleanly with no orphaned records

## 6.4 Smoke test checklist

Critical user-facing flows to verify before declaring the deployment complete: [list the flows specific to Patatte here, e.g. account login, core transaction flow, order/status update, payment confirmation].

- [Flow 1]

- [Flow 2]

- [Flow 3]

# 7. Rollback Procedure

If a rollback trigger from Section 5.3 is hit, follow this procedure rather than attempting to patch forward under pressure.

- Re-enable maintenance mode / drain traffic immediately.

- If the development team has confirmed a reverse script (Section 2) and no destructive step has run yet, execute the reverse script.

- If a destructive or non-reversible step has already run, restore the pre-migration backup to a scratch instance, verify it, then cut production over to it.

- Redeploy the previous known-good application release via the standard deployment pipeline.

- Re-run smoke tests (6.4) against the restored/rolled-back state.

- Disable maintenance mode.

- Announce the rollback to stakeholders with a brief cause summary.

- Schedule a retro with the development team before re-attempting the migration.

# 8. Communication Plan

| When | Audience | Channel | Message |
| --- | --- | --- | --- |
| T-2 days | Stakeholders | [channel] | Deployment window scheduled for [date/time], expected downtime [X min or none] |
| T-1 hour | Internal team | [channel] | Final go/no-go confirmation, backup verified |
| T-0 (start) | Users, if downtime expected | [status page / in-app banner] | Maintenance in progress |
| T-0 (end) | Stakeholders | [channel] | Deployment complete, systems verified |
| If rollback | Stakeholders | [channel] | Issue encountered, rolled back to previous state, no data loss, retro scheduled |

# 9. Sign-Off

This migration does not run against production until every item below is checked and signed.

| Item | Confirmed by | Date |
| --- | --- | --- |
| Section 2 intake complete |  |  |
| Risk classification agreed (Section 3) |  |  |
| Backup taken & restore-tested |  |  |
| Deployment window communicated |  |  |
| Rollback owner assigned |  |  |
| Final go-ahead |  |  |

Appendix: attach the migration script/change files, the pre-migration schema snapshot, and the dev team's test-run confirmation as supporting references.